Republic of the Philippines



**Department of Education**

Region XII

**COTABATO DIVISION**

Amas, Kidapawan City

**ABOT-ALAM MULTI-STAKEHOLDERS ALLIANCE**

**SY 2015-2016**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **COMPONENT** | **STRATEGIES** | **RESPONSIBLE PERSON/S/Partners** | **TIME FRAME** | **EXPECTED OUTPUT** |
| **Advocacy, Social Mobilization and Communication** | * **Prepare the following radio program:**   -Radio Plug/advertisement of Abot-Alam  -Updates of the Abot-Alam Program  -Success stories of Abot-Alam recipients  -30-minute Radio-Based Instruction  (RBI) Program for ALS-Abot Alam    -TESDA/DTI/LGU/PESO/DSWD Radio  program and support   * **Broadcast the following program over dxGO 103.1 dream fm station of DepED-ALS Cotabato Division, Amas, Kidapawan City which is Financially Supported by Provincial Government**   -Radio Plug/advertisement of Abot-Alam  -Updates of the Abot Alam Program  -Success stories of Abot Alam recipients  -30-minute Radio-Based Instruction  (RBI)Program for ALS-Abot Alam  -TESDA/DTI/LGU/PESO/DSWD/  program and support   * **Continues Referral of Abot-Alam Learners to Partner Agencies**   **-**Submission of second batch of learners to partner agencies for livelihood/skills training/entrepreneurship/scholarship and employment  -Acceptance of learners by partner agencies  -Provision of support to learners | EPS-1 , EPSA, ALS-Abot Alam Implementers  ALS Abot Alam Implementers  TESDA/DTI/PESO/DSWD  Radio Announcers provided by the Provincial Government and Selected ALS-Abot Alam Implementers  TESDA/DTI/LGU/PESO/DSWD  Abot-Alam Implementers  LGUs and Partner Agencies  LGUs and Partner Agencies | June 2015  June to December 2016    July 2015 to March 2016  July to August 2015 | Advocated Abot Alam Program  Gained more support from stakeholders  Provided continues intervention to OSY in terms of education, entrepreneurship and employment |
| **Launching Program** | * **Conduct Launching Program of the Second Batch of Learners for Skills Training**   -Invite stakeholders  -Sign MOA/MUA with new partner agencies  -Launch the skills training | DepEd and Abot Alam Multi-Stakeholders | Last Week of August 2015 | Formalized and recognized stakeholders support |
| **Online Submission of Abot Alam Learners to LIS** | * **Train/Orient the Abot-Alam Implementers on Online Submission of learners to LIS** * **Online submission of learners** | DepEd: ALS-Abot Alam Implementers and partners | July 2015 | Issued LRN to learners |
| **Capability Building** | * **Train newly hired Literacy Workers**   **-**Prepare training design  -Allocate budget  -Issue memo for the participants  -Conduct capability building | DepEd: SDS, ASDS, Accounting, EPS-1 and 5 EPSA | June 2015 | Equipped Abot Alam Implementers of the necessary skills |
| **Provision of Learning Materials** | * **Reproduce and Deliver Instructional Materials for the Abot Alam Learners**   -Coordinate with LGUS and partner agencies on the development of localized materials for livelihood/ entrepreneurship/ skills training for **face to face interaction** and to be aired over the radio  -Allocate/provide/reproduce support materials for Abot-Alam learners by partner agencies | DepEd and Multi-Stakeholders Alliance | August 2015 | Provided learners with adequate and appropriate learning materials |
| **Access to A&E Test** | * **Register Abot-Alam Learners to 2015 A&E Test** * **Reproduce and deliver practice test materials/parallel A&E test to registered test takers**   **-**Develop A&E parallel test  **-**Use Parallel A&E test during review session | ALS- Abot Alam Implementers  ALS- Abot Alam Implementers and Multi-Stakeholders  ALS-Abot Alam Implementers | July to August 2015  September 2015 | Registered Abot Alam Learners to 2015 A&E |
| **Other Support Program to Abot-Alam Learners** | * **Conduct Sports Festival to Abot Alam Learners**     -Coordinate with the partners for the sports festival  -Provide sports equipment, transportation and other logistics for the successful sports festival   * **Conduct Drug Symposium and other Information Drive**   -Coordinate with partner agencies  -Invite resource persons | DepEd and Multi-Stakeholders Alliance | April 2016 | Provided opportunities for the learners to develop and improve interpersonal relationship and sportsmanship |
| **Monitoring, Evaluation and Plan Adjustment** | * **Conduct ALS-Abot Alam Cluster Monitoring, Evaluation and Plan Adjustment (ALS-Abot Alam CMEPA)**   **-**Prepare status of Abot-Alam Program in terms of learning interventions, skills training, entrepreneurship/employment  -Invite stakeholders and partner agencies (LGU-Chairmen of Committee on Education(Municipal/Barangay Levels, TESDA, DTI, PESO**)**  **-**Sharing of Updates (DepEd and Partner Agencies on the Status of Abot Alam Program in respective municipalities | EPS-1/EPSA/Abot-Alam Implementers (Literacy Volunteers/Excess Teachers)  DepEd and Multi-Stakeholders Alliance  DepEd and Multi-Stakeholders Alliance | June 2015,  Sept. 2015  December  2015  March 2016 | Updated stakeholders of the status of Abot Alam Program, clarified Issues and concerned and generate more support through plan adjustment |
| **AWARD AND RECOGNITION** | * **Conduct search of Outstanding Abot Alam Learners and Partners/Stakeholders**   -Prepare criteria  -Finalize the criteria  -Conduct the search   * **Recognize Outstanding learners/Partners** | DepEd and Multi-Stakeholders Alliance | April 2016 | Recognized outstanding learners and stakeholders |

**Prepared by: DepEd-ALS and Multi-Stakeholders Alliance on Abot Alam Program**

Cotabato Province

Respectfully Submitted:

**DR. JULIE B. LUMOGDANG**

EPS-1

Focal Person on ALS-Abot Alam Program

**APPROVED:**

**OMAR A. OABS, CESO VI**

Schools Division Superintendent