Republic of the Philippines

**Department of Education**

Region XII

**COTABATO DIVISION**

Amas, Kidapawan City

**ABOT-ALAM MULTI-STAKEHOLDERS ALLIANCE**

**SY 2015-2016**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **COMPONENT** | **STRATEGIES**  | **RESPONSIBLE PERSON/S/Partners**  | **TIME FRAME**  | **EXPECTED OUTPUT**  |
| **Advocacy, Social Mobilization and Communication** | * **Prepare the following radio program:**

-Radio Plug/advertisement of Abot-Alam -Updates of the Abot-Alam Program -Success stories of Abot-Alam recipients-30-minute Radio-Based Instruction  (RBI) Program for ALS-Abot Alam -TESDA/DTI/LGU/PESO/DSWD Radio  program and support * **Broadcast the following program over dxGO 103.1 dream fm station of DepED-ALS Cotabato Division, Amas, Kidapawan City which is Financially Supported by Provincial Government**

-Radio Plug/advertisement of Abot-Alam -Updates of the Abot Alam Program -Success stories of Abot Alam recipients-30-minute Radio-Based Instruction  (RBI)Program for ALS-Abot Alam -TESDA/DTI/LGU/PESO/DSWD/  program and support* **Continues Referral of Abot-Alam Learners to Partner Agencies**

**-**Submission of second batch of learners to partner agencies for livelihood/skills training/entrepreneurship/scholarship and employment-Acceptance of learners by partner agencies -Provision of support to learners  | EPS-1 , EPSA, ALS-Abot Alam ImplementersALS Abot Alam ImplementersTESDA/DTI/PESO/DSWD Radio Announcers provided by the Provincial Government and Selected ALS-Abot Alam ImplementersTESDA/DTI/LGU/PESO/DSWDAbot-Alam ImplementersLGUs and Partner Agencies LGUs and Partner Agencies   | June 2015 June to December 2016  July 2015 to March 2016July to August 2015  | Advocated Abot Alam Program Gained more support from stakeholdersProvided continues intervention to OSY in terms of education, entrepreneurship and employment  |
| **Launching Program**  | * **Conduct Launching Program of the Second Batch of Learners for Skills Training**

-Invite stakeholders -Sign MOA/MUA with new partner agencies -Launch the skills training  | DepEd and Abot Alam Multi-Stakeholders  | Last Week of August 2015  | Formalized and recognized stakeholders support  |
| **Online Submission of Abot Alam Learners to LIS** | * **Train/Orient the Abot-Alam Implementers on Online Submission of learners to LIS**
* **Online submission of learners**
 | DepEd: ALS-Abot Alam Implementers and partners  | July 2015 | Issued LRN to learners  |
| **Capability Building**  | * **Train newly hired Literacy Workers**

**-**Prepare training design -Allocate budget -Issue memo for the participants -Conduct capability building  | DepEd: SDS, ASDS, Accounting, EPS-1 and 5 EPSA  | June 2015  | Equipped Abot Alam Implementers of the necessary skills |
| **Provision of Learning Materials**  | * **Reproduce and Deliver Instructional Materials for the Abot Alam Learners**

-Coordinate with LGUS and partner agencies on the development of localized materials for livelihood/ entrepreneurship/ skills training for **face to face interaction** and to be aired over the radio -Allocate/provide/reproduce support materials for Abot-Alam learners by partner agencies  | DepEd and Multi-Stakeholders Alliance | August 2015  | Provided learners with adequate and appropriate learning materials |
| **Access to A&E Test**  | * **Register Abot-Alam Learners to 2015 A&E Test**
* **Reproduce and deliver practice test materials/parallel A&E test to registered test takers**

**-**Develop A&E parallel test**-**Use Parallel A&E test during review session | ALS- Abot Alam Implementers ALS- Abot Alam Implementers and Multi-Stakeholders ALS-Abot Alam Implementers  | July to August 2015 September 2015  | Registered Abot Alam Learners to 2015 A&E  |
| **Other Support Program to Abot-Alam Learners**  | * **Conduct Sports Festival to Abot Alam Learners**

-Coordinate with the partners for the sports festival -Provide sports equipment, transportation and other logistics for the successful sports festival * **Conduct Drug Symposium and other Information Drive**

-Coordinate with partner agencies -Invite resource persons  | DepEd and Multi-Stakeholders Alliance | April 2016 | Provided opportunities for the learners to develop and improve interpersonal relationship and sportsmanship |
| **Monitoring, Evaluation and Plan Adjustment**  | * **Conduct ALS-Abot Alam Cluster Monitoring, Evaluation and Plan Adjustment (ALS-Abot Alam CMEPA)**

**-**Prepare status of Abot-Alam Program in terms of learning interventions, skills training, entrepreneurship/employment-Invite stakeholders and partner agencies (LGU-Chairmen of Committee on Education(Municipal/Barangay Levels, TESDA, DTI, PESO**)****-**Sharing of Updates (DepEd and Partner Agencies on the Status of Abot Alam Program in respective municipalities  | EPS-1/EPSA/Abot-Alam Implementers (Literacy Volunteers/Excess Teachers) DepEd and Multi-Stakeholders AllianceDepEd and Multi-Stakeholders Alliance | June 2015, Sept. 2015 December 2015 March 2016  | Updated stakeholders of the status of Abot Alam Program, clarified Issues and concerned and generate more support through plan adjustment |
| **AWARD AND RECOGNITION**  | * **Conduct search of Outstanding Abot Alam Learners and Partners/Stakeholders**

-Prepare criteria -Finalize the criteria -Conduct the search * **Recognize Outstanding learners/Partners**
 | DepEd and Multi-Stakeholders Alliance | April 2016  | Recognized outstanding learners and stakeholders |

**Prepared by: DepEd-ALS and Multi-Stakeholders Alliance on Abot Alam Program**

 Cotabato Province

Respectfully Submitted:

 **DR. JULIE B. LUMOGDANG**

 EPS-1

 Focal Person on ALS-Abot Alam Program

 **APPROVED:**

 **OMAR A. OABS, CESO VI**

 Schools Division Superintendent